## Sheet 1 - roll_out_2021-07-25
roll_out_2021-07-25
deployment | activity | start_connx | finish_connx | premises
Cavan | Network Build In Progress | 2021-01-01 | 2021-06-30 | 3738
Carrigaline | Network Build In Progress | 2021-07-01 | 2021-08-31 | 4615
Galway | Network Build In Progress | 2021-07-01 | 2021-09-30 | 3502
Ballinasloe | Network Build In Progress | 2021-08-01 | 2021-09-30 | 3307
Limerick | Network Build In Progress | 2021-07-01 | 2021-09-30 | 4075
Tralee | Network Build In Progress | 2021-07-01 | 2021-09-30 | 3167
Monaghan | Network Build In Progress | 2021-07-01 | 2021-09-30 | 4355
Wexford | Network Build In Progress | 2021-11-01 | 2022-01-31 | 3745
Killarney | Network Build In Progress | 2021-11-01 | 2022-01-31 | 3382
Roscommon | Network Build In Progress | 2021-11-01 | 2021-12-31 | 3591
Tipperary | Network Build In Progress | 2021-11-01 | 2021-12-31 | 3316
Dundalk | Network Build In Progress | 2021-08-01 | 2021-10-31 | 2770
Sligo | Network Build In Progress | 2021-12-01 | 2022-01-31 | 2513
Kilcoole | Network Build In Progress | 2021-12-01 | 2022-01-31 | 2836
Castlebar | Network Build In Progress | 2021-12-01 | 2022-01-31 | 2139
Mullingar | Network Build In Progress | 2022-01-01 | 2022-03-31 | 4109
Blessington | Network Build In Progress | 2022-01-01 | 2022-04-30 | 5031
Carlow | Network Build In Progress | 2021-10-01 | 2022-01-31 | 3544
Midleton | Network Build In Progress | 2022-02-01 | 2022-05-31 | 8446
Skerries | Network Build In Progress | 2022-01-01 | 2022-04-30 | 2437
Ballina | Network Build In Progress | 2022-01-01 | 2022-04-30 | 2678
Clonmel | Network Build In Progress | 2022-01-01 | 2022-04-30 | 2143
Gort | Network Build In Progress | 2022-01-01 | 2022-04-30 | 2618
Waterford | Network Build In Progress | 2022-01-01 | 2022-04-30 | 6351
Drogheda | Network Build In Progress | 2022-01-01 | 2022-04-30 | 4173
Athlone | Survey Underway | 2022-01-01 | 2022-03-31 | 2160
Youghal | Survey Underway | 2022-01-01 | 2022-03-31 | 3371
Enniskerry | Survey Underway | 2022-01-01 | 2022-03-31 | 2262
Inverin | Survey Underway | 2022-01-01 | 2022-03-31 | 1075
Roscrea | Survey Underway | 2022-02-01 | 2022-04-30 | 2415
Portlaoise | Survey Underway | 2022-02-01 | 2022-04-30 | 3638
Carrick-on-Shannon | Survey Underway | 2022-02-01 | 2022-04-30 | 3576
Longford | Survey Underway | 2022-03-01 | 2022-05-31 | 3294
Athenry | Survey Underway | 2022-03-01 | 2022-05-31 | 2026
Dunboyne/Clonee | Survey Underway | 2022-04-01 | 2022-06-30 | 4455
Ballycarney | Survey Underway | 2022-04-01 | 2022-06-30 | 4252
Loughrea | Survey Underway | 2022-05-01 | 2022-07-31 | 2386
Letterkenny | Survey Underway | 2022-06-01 | 2022-08-31 | 3118
Castlegregory | Survey Underway | 2022-06-01 | 2022-08-31 | 886
Ballydavid | Survey Underway | 2022-06-01 | 2022-08-31 | 1816
Kilkenny | Survey Underway | 2022-07-01 | 2022-12-31 | 2952
Kilkishen | Survey Underway | 2022-07-01 | 2022-12-31 | 3556
Adare | Survey Underway | 2022-07-01 | 2022-12-31 | 4508
Johnstown | Survey Underway | 2022-07-01 | 2022-12-31 | 2999
Borris | Survey Underway | 2022-07-01 | 2022-12-31 | 4228
Delvin | Survey Underway | 2022-07-01 | 2022-12-31 | 2387
Tomhaggard | Survey Underway | 2022-07-01 | 2022-12-31 | 3234
Cashel | Survey Underway | 2022-07-01 | 2022-12-31 | 2044
Kilgarvan | Survey Underway | 2022-07-01 | 2022-12-31 | 2086
Creeslough | Survey Underway | 2022-07-01 | 2022-12-31 | 3271
Riverstown RVN | Survey Underway | 2022-07-01 | 2022-12-31 | 907
Ballyheigue | Survey Underway | 2022-08-01 | 2022-10-31 | 1562
Emyvale | Survey Underway | 2022-11-01 | 2023-01-31 | 1320
Clones | Survey Underway | 2022-11-01 | 2023-01-31 | 1746
Redcross | Survey Underway | 2022-11-01 | 2023-01-31 | 3236
Newport (MO) | Survey Underway | 2023-01-01 | 2023-12-31 | 1826
Castlegarron | Survey Underway | 2023-01-01 | 2023-12-31 | 1446
Rathmore | Survey Underway | 2023-01-01 | 2023-03-31 | 3483
Ballylinan | Survey Underway | 2023-02-01 | 2023-04-30 | 3343
Carrickmacross | Survey Underway | 2023-01-01 | 2023-12-31 | 3223
Curragh Camp | Survey Underway | 2023-01-01 | 2023-12-31 | 2659
Carrick-on-Suir | Survey Underway | 2023-01-01 | 2023-12-31 | 4926
Castlerea | Survey Underway | 2023-01-01 | 2023-12-31 | 4677
Mountrath | Survey Underway | 2023-01-01 | 2023-12-31 | 2714
Navan | Survey Underway | 2023-01-01 | 2023-12-31 | 3396
Templemartin | Survey Underway | 2023-01-01 | 2023-12-31 | 6333
Rutland Island, Burtonport (DL) | Survey Planned | 2022-11-01 | 2023-01-31 | 7
Inishfree Island, Burtonport (DL) | Survey Planned | 2022-11-01 | 2023-01-31 | 21
Valentia | Survey Planned | 2022-07-01 | 2022-12-31 | 119
Arranmore | Survey Planned | 2022-11-01 | 2023-01-31 | 470
Carrowholly, Westport (MO) | Survey Planned | 2023-01-01 | 2023-12-31 | 5
Killadoon | Survey Planned | 2023-01-01 | 2023-12-31 | 1008